# MATCH WORD - Developer Proposal & Milestone Quote

Prepared for: Ronna McKenzie / Grandma Mac (grandmamac.com)
Prepared by: Gregory H. (@HamparProd)
Spec reference: Match Word Developer Technical Specification, Version 2.0 (June 29, 2026)
Date: June 29, 2026 (Revised — MVP scope agreed at $6,000 CAD)
Currency: All prices in CAD
Engagement type: Fixed-price, milestone-based — payment released only on review and approval
Communication: Freelancer platform chat only

## 1. Summary

Thank you for sharing the full specification. I have read all 23 sections carefully. Below is my proposed
build plan: a recommended technology stack, a milestone-by-milestone fixed price, an estimated timeline,
and the assumptions the quote depends on.

The plan follows your milestone order exactly so each payment maps to a clearly demonstrable deliverable.
Every screen is built to your non-negotiable senior-friendly standards (18pt+ body text, 22pt+ game
actions, 48x48pt tap targets, high contrast, one primary action per screen, no ads, and the word "AI"
never shown anywhere in the app).

Total fixed price: $6,000 CAD across 9 MVP milestones.
Estimated build duration: ~11–13 working weeks (single developer, sequential milestones).

This revised plan fits the agreed $6,000 budget by deferring a clear block of retention/polish features to
Phase 2 (built once Match Word is live and subscription revenue is coming in — see Section 4). The full
core game-show experience — characters, lobby, complete gameplay, Guy Smiley host, billing, and store
launch — all remains in the MVP.

## 2. Recommended Technology Stack

| Layer | Recommendation | Why |
| --- | --- | --- |
| App framework | Flutter (Dart) | Single codebase for iOS + Android, excellent for image-layered/paper-doll UI, smooth animation, strong on small screens (iPhone SE). |
| Backend / Realtime | Supabase (Postgres + Realtime + Auth + Storage) | Server-authoritative game state, realtime sync of clues/guesses, secure storage of email + device fingerprints, generous free tier for MVP. |
| Realtime gameplay | Supabase Realtime channels (WebSocket-based) | Reliable multi-screen sync for clues, guesses, turns, and lobby state. |
| Voice input | Native iOS SFSpeechRecognizer / Android SpeechRecognizer | No per-use cost, on-device, fast. Text fallback always available per spec §12. |
| Guy Smiley voice (TTS) | Pre-recorded clips for fixed lines + ElevenLabs for generated lines | Pre-recorded keeps quality high and cost predictable; ElevenLabs used for dynamic announcements. Final approach confirmed with you before §6 work. |
| Subscriptions | Apple StoreKit 2 (iOS) + Google Play Billing (Android) | Native billing as required; 7-day trial with no card up front. |
| Auth model | First name + 4-digit PIN, email used only for PIN recovery | Exactly as specified — familiar and simple for seniors. |

Note on "no credit card required" trial: the 7-day trial, in-app countdown, and access gating are fully
under our control. The store checkout flow itself is controlled by Apple/Google. Configured correctly,
the trial starts with no card required; I will confirm the exact store configuration during Milestone 9.

## 3. Milestone Pricing & Timeline (MVP — $6,000 CAD)

| # | Milestone | Key Deliverables | Est. Days | Price (CAD) |
| --- | --- | --- | --- | --- |
| 1 | Sign In & Account System | First name + 4-digit PIN login, one-time email capture, Forgot-PIN email reset flow, device-ID fingerprint trial-abuse prevention (silent). (IP-based layer → Phase 2.) | 5–7 | $550 |
| 2 | Opening Screen & Navigation | App shell + navigation, Guy Smiley greeting screen, Check Upcoming Games + Enter the Studio buttons, senior-friendly design system (fonts, contrast, tap targets) established here. | 4–5 | $400 |
| 3 | Character Creation System | 7-step one-choice-per-screen wizard, paper-doll assembly from client PNG layers, name-on-shirt, preview/confirm, save to profile, edit later. | 6–7 | $650 |
| 4 | Lobby & Game Codes | Create game + 4-digit code, join by code, Check Upcoming Games list, role assignment (Player 1/2/A/B), team formation, AI seat-fill. (Solo stranger matchmaking → Phase 2.) | 7–8 | $600 |
| 5 | Core Gameplay Engine | Server-authoritative turn system, dual input (voice + text) for clues & guesses, clue/guess visible to all, steal mechanic, ~5-exchange word reveal, scoring, first half / halftime / second half, role switch. | 12–14 | $1,350 |
| 6 | Guy Smiley Host + Audio System | Host character with voice + idle animations, rules intro every game, round announcements, theme music + announcer intro, applause/cheer SFX, full disconnect alarm (red flash + ALERT + AWOOGA horn), mute/volume control, silent-mode respect. (MVP uses pre-recorded clips; ElevenLabs dynamic lines → Phase 2.) | 8–9 | $750 |
| 7 | AI Characters | AI clue-giving/guessing logic (moderate difficulty) + a fun starter idle-animation set. (Full animation library + in-game friend-request flow → Phase 2.) | 6–7 | $450 |
| 8 | Subscription Billing & Free Trial | $5.99/mo products on both stores, 7-day no-card trial, Day-3 countdown timer, warm Day-7 prompt, access gating after trial. | 7–9 | $800 |
| 9 | Testing, Bug Fixes & Store Submission | QA pass, senior-usability checks, performance testing on small screens, bug fixes, Apple App Store + Google Play submission support. | 6–8 | $450 |
|  | TOTAL |  | ~61–74 days | $6,000 |

Timeline assumes one milestone at a time, sequential. Days are working days. Calendar duration is longer
due to your scheduled-update / weekday / weekends-off working agreement, which I fully respect.

## 4. What's Included

- Cross-platform iOS + Android app from a single Flutter codebase

- Server-authoritative game logic (game state managed server-side, not client-only)

- Senior-friendly UI standards applied to every screen (§4 compliance)

- Proof of work (screenshots / test builds) before each milestone payment is released

- Clean, version-controlled (Git) delivery

- Full ownership of all code, assets, and IP transferred to client (§23)

## 5. Assumptions & Client-Provided Items

To keep pricing accurate, the quote assumes the client provides the following (as stated in the spec):

- All character art as layered PNG files (bases, hair, eyes, glasses, outfits) — §8

- AI idle animation assets — the starter set for MVP, full library in Phase 2 — §11

- Guy Smiley character art and any reference avatars — §5

- Brand assets and colours (#5B2D8E etc.) — §5

- Trophy and prize art in clay style — §18 (Phase 2)

The developer will source licensed theme music + announcer audio (warm, classic game-show style) as
part of the MVP — §16. The developer builds the assembly, rendering, logic, and integration systems around
the client-provided assets.

The developer builds the assembly, rendering, logic, and integration systems around these assets.

## 6. Phase 2 — Deferred Features (built once subscription revenue begins)

To fit the agreed $6,000 CAD budget, the following features are deferred to Phase 2. None of them are
part of the core game-show loop — they are retention and polish features that make the most sense to add
once players are subscribing. Each can be quoted as its own milestone when you're ready.

| Deferred feature | Spec ref | Indicative Phase 2 price (CAD) |
| --- | --- | --- |
| Prize Room & Trophy System (display room, earning logic, expansion) | §18 | ~$550 |
| Solo stranger matchmaking + in-game friend-making | §9, §17 | ~$450 |
| Full AI idle-animation library (MVP ships a fun starter set) | §11 | ~$400 |
| ElevenLabs dynamic Guy Smiley announcements (MVP uses warm pre-recorded clips) | §14 | ~$300 |
| IP-based trial-abuse layer (MVP uses device-ID fingerprinting) | §6 | ~$150 |
| Physical mailed trophies (already Phase 2 in your spec) | §18 | TBD |

The MVP still delivers the complete experience players see and feel: characters, studio, teams, clues,
guesses, steals, scoring, Guy Smiley host with voice, the disconnect alarm, billing, and store launch.

## 7. Out of Scope (not planned)

- Tournament bracket system (beyond basic trophy milestone)

- Advanced AI behaviour beyond "moderate difficulty" baseline

- Backend infrastructure costs (Supabase paid tier, ElevenLabs usage, Apple/Google developer accounts) — these are operating costs billed to the client's own accounts, not developer fees

- Localization / multi-language support

## 8. Payment & Working Terms

- Fixed price per milestone, agreed before that milestone begins

- No full payment up front; each milestone is funded, then built, then reviewed, then released

- Proof of work provided before each release

- Any scope change agreed in writing before work begins (§23)

- All communication on Freelancer platform chat only; questions grouped into scheduled updates; weekends respected

- Prices quoted in CAD to match your Freelancer budget

## 9. Starting Point

We begin with Milestone 1 (Sign In & Account System) as agreed. The senior-friendly design system
(fonts, contrast, tap targets) is established in Milestone 2 so you can approve the visual direction early.

## 10. Confirmed Decisions

1. Tech stack — Flutter + Supabase (confirmed; client already uses Supabase elsewhere).

2. Guy Smiley voice — Mix of pre-recorded clips + ElevenLabs for dynamic lines (ElevenLabs dynamic layer scheduled for Phase 2).

3. Audio assets — Developer to source licensed audio for theme music + announcer (warm, fun, classic game-show style).

4. Asset delivery — Client is preparing character art now; ready before the dependent milestones (3, 6, 7).

5. Starting milestone — Milestone 1 confirmed.

Honesty note (per spec §2): I have flagged the Apple/Google trial-checkout nuance and the dependency on
client-provided art/audio assets up front. I am confident in delivering every component to the standard
described. If any asset or scope detail shifts during the build, I will raise it immediately rather than
absorb it silently.